FICTITIOUS DEMONSTRATION SAMPLE

Monthly service performance report

FICTITIOUS DEMONSTRATION SAMPLE. Every company, person, work order, source, and result is invented. This report concerns only civilian request-intake and service operations.

# Administrative data

| Field | Report value |
| --- | --- |
| Contractor | Meridian Support Services, Inc. |
| Work order | DCS-SVC-2026-01 |
| Report type | Monthly service performance report |
| Reporting period | 01 June through 30 June 2026 |
| Report date | 07 July 2026 |
| Prepared for | Fictitious Civic Services Office |
| Prepared by | Meridian Support Services, Inc. |

# Executive snapshot

Meridian reported June work under all five service requirements. Five named contributors covered request intake, queue control and customer routing, document quality, knowledge-base quality, and the monthly dashboard.

| Performance area | June result |
| --- | --- |
| Request intake | 1,642 incoming requests validated; 1,611 routed to service queues; 31 returned for required information |
| Queue control and customer routing | Queue older than five business days reduced from 82 requests to 36; median routing time reduced from 1.6 to 1.3 business days |
| Document quality | 684 request records reviewed; 681 complete at first review, or 99.6%; remaining 3 corrected before the dashboard |
| Knowledge-base quality | 24 approved articles updated; 7 obsolete articles retired; 43 staff routing questions answered using the approved knowledge base |
| Monthly dashboard | June request-intake and queue-aging dashboard delivered on schedule with all six required service measures |

# Service-requirement coverage

| Requirement | June coverage | Contributor |
| --- | --- | --- |
| SO-1, request intake | Validate incoming requests, route complete requests, and return requests that lack required information | Avery Chen |
| SO-2, queue control and customer routing | Monitor aged requests, adjust routing, and report median routing time | Marcus Reyes |
| SO-3, document quality | Check required fields, record corrections, and confirm completeness before dashboard reporting | Elena Park |
| SO-4, knowledge-base quality | Update approved articles, retire obsolete content, and answer routing questions with current guidance | Yolanda Briggs |
| SO-5, monthly dashboard | Review and deliver the monthly service dashboard on schedule | Sarah Whitfield |

# Contributor performance

## Avery Chen, Workflow Analyst

Avery validated 1,642 incoming requests, routed 1,611 to service queues, and returned 31 for required information.

## Marcus Reyes, Workflow Lead

Marcus reduced the queue older than five business days from 82 requests to 36 and reduced median routing time from 1.6 to 1.3 business days.

## Elena Park, Data Quality Specialist

Elena reviewed 684 request records. At first review, 681 contained all required fields, for 99.6 percent completeness. She corrected the remaining 3 records before the monthly dashboard.

## Yolanda Briggs, Quality and Knowledge Lead

Yolanda updated 24 approved knowledge articles, retired 7 obsolete articles, and answered 43 staff routing questions using the approved knowledge base.

## Sarah Whitfield, Program Manager

Sarah delivered the June request-intake and queue-aging dashboard on schedule. It included request volume, one-business-day triage, aged backlog, document completeness, knowledge-base changes, and median routing time.

# Significant accomplishments

The queue older than five business days declined from 82 requests to 36.

Median routing time declined from 1.6 to 1.3 business days.

Required-field completeness was 99.6 percent at first review, and all 3 incomplete records were corrected before dashboard reporting.

The monthly dashboard was delivered on schedule with the required request, queue, document, knowledge, and routing measures.

# Items to monitor

Thirty-one incoming requests were returned for required information before routing.

Seven obsolete knowledge articles were retired so staff would use current routing guidance.

# Deliverable status

| Deliverable | June status | Coverage |
| --- | --- | --- |
| Monthly service performance report | Complete for client review | SO-1 through SO-5 addressed |

The report covers the June request-intake, queue, document-quality, knowledge-base, customer-routing, and dashboard results supported by the fictional source record.

# Next reporting period

Meridian will continue the five service activities during the next reporting period:

Validate and route incoming service requests.

Monitor queue age and customer-routing time.

Review required fields and document corrections.

Maintain approved knowledge articles and routing guidance.

Deliver the monthly service dashboard with the applicable measures.

# Review record

| Review item | Record |
| --- | --- |
| Reporting period end | 30 June 2026 |
| Management review | Sarah Whitfield, 06 July 2026 |
| Fictional customer review | Completed 07 July 2026 |